## 1 — Diagnosis
Diagnosis — Four Planted Failure Modes (10.W.5.draft.md fallback)
Failure mode | Defect in draft | Fix applied in this workbook
1 — Contingency inside margin | Draft had one line: 'Overhead & profit: 22%'. Risk reserve and profit were a single number — any negotiation cut removes both simultaneously; neither is visible or defensible separately. | Split into two named lines: Contingency (8% of delivery costs, sized from risk register expected-value × 2× tail-risk factor) and Margin (11% of revenue, profit target). See Summary tab lines 16–17.
2 — Risk with no mitigation | Draft risk register had: 'Key person departure — L:3 I:4 — Mitigation: TBD'. An unmitigated risk is a complaint. A buyer who reads 'TBD' at bid stage has a valid ground to reject the submission. | All 5 risks in the register now have active mitigations. Key person departure: EPAM names one pre-approved backup per key role in the proposal; substitution requires Meridian approval within 3 business days. See Risk Register tab.
3 — Unbounded assumption | Draft assumption register had: 'The team will integrate with SAP efficiently.' This is unfalsifiable — no number, no named condition, no consequence if false. It protects nothing. | All 5 assumptions now bounded numerically or by a named condition with an explicit consequence. Example: 'SAP integration design complete within 10 business days of credential receipt; if >15 days, Phase 1 extends day-for-day at no extra cost — EPAM bears.' See Assumption Register tab.
4 — T&M vs. fixed-price RFP | Draft recommended 'Time & Materials — standard EPAM engagement model.' RFP §7 submission rules states: 'commercial proposal '— fixed-price or capped T&M; no open-ended T&M' and lists open-ended T&M as a disqualifying condition. | Commercial model changed to Hybrid: Phase 0 fixed-fee €33K (gated, discovery only) + Phases 1–3 capped T&M at €307K cap with explicit change-control triggers (root-cause gate scope change, POS data restriction). EPAM carries cost risk within the cap; Meridian carries scope-change risk. See Commercial tab.

## 2 — Summary
Estimate Summary — Meridian UC1.1 Pilot (Balanced Variant, 12 weeks)
Line item | Notes | Amount (€)
A. EPAM Delivery Effort
Engagement Lead (onshore, 1.75 FTE-months) | Blended across 3 phases | 38500
Solution Architect (onshore, 1.25 FTE-months) | Phases 0–1 only; SAP gate | 26250
Data Engineer 1 (nearshore, 2.50 FTE-months) | Phases 0–3 | 38750
Data Engineer 2 (nearshore, 1.55 FTE-months) | Phases 1–3 | 24025
ML Engineer (nearshore, 1.75 FTE-months) | Phases 1–3 | 26250
Project Manager (nearshore, 3.00 FTE-months) | Full engagement | 40500
QA / BI Analyst (nearshore, 1.00 FTE-months) | Phases 2–3 | 12500
B. Delivery Impact Adjustments
Ramp adjustment (−10% Month 1 productivity) | Standard ramp; reduces effective effort | -2028
Dependency wait — SAP credential delay buffer | 3-day buffer at EL + SA rate; A2 bound | -1000
OCM coordination overhead | EPAM PM ×4 hrs/week × 3 months | 2430
EPAM delivery subtotal (before overhead) |  | 206177
EPAM management overhead (10%) | Bid mgmt, transition, internal QA | 20617.7
C. Third-Party & Expenses
OCM sub-vendor (Prosci — fixed fee, pass-through) | Workshops × 2, adoption plan | 35000
Travel & client-site expenses | Estimated 4 site visits | 12000
Licences & tooling | GitHub Copilot × 6 + EPAM DIAL dev tools; AI unit cost sourced from M800: $2.50/M input, $10/M output; dev usage ~500K tokens/month → €130 | 6000
Delivery subtotal (before contingency and margin) |  | 279794.7
D. CONTINGENCY (separate from margin — risk-register-sized, not a flat rule-of-thumb)
Contingency (8% of delivery subtotal) | Sized: 5 risks × expected-value × 2× tail factor = €22K; capped at 8% of subtotal. Separate from margin. Source: Risk Register tab. | 22383.576
E. MARGIN (profit target — separate from contingency)
Margin (11% of total revenue — profit target) | Strategic new-logo rate; standard target 20%; reduced for pilot referenceability. Negotiation can cut margin but NOT contingency. | 37347.8768
TOTAL PROPOSAL PRICE (all-in) | Within RFP §4 €250K–€350K envelope | 339526.1528

## 3 — Effort by Phase
Effort by Role × Phase — Balanced Variant (person-days; 22 days/month)
Role | Phase 0 (wks 1–2) Discovery | Phase 1 (wks 3–5) Data foundation | Phase 2 (wks 6–10) Build & interface | Phase 3 (wks 11–12) Measurement | Total person-days | Cost (€)
Engagement Lead (onshore) | 8.2 | 12.4 | 13.8 | 5.5 | 39.9 | 39875
Solution Architect (onshore) | 8.2 | 12.4 | 6.9 | 0 | 27.5 | 26250
Data Engineer 1 (nearshore) | 3.3 | 12.4 | 27.5 | 11 | 54.2 | 38168.75
Data Engineer 2 (nearshore) | 2.2 | 8.2 | 20.6 | 5.5 | 36.6 | 25768.75
ML Engineer (nearshore) | 0 | 4.1 | 24.1 | 11 | 39.2 | 26718.75
Project Manager (nearshore) | 11 | 16.5 | 27.5 | 11 | 66 | 40500
QA / BI Analyst (nearshore) | 0 | 0 | 11 | 8.2 | 19.2 | 10937.5
TOTAL | 33 | 66 | 131.3 | 52.2 | 282.5 | 208218.75
Delivery impact adjustments applied to Summary tab: ramp −10% month 1 (€−2,028); SAP credential delay buffer (€−1,000); OCM coordination overhead (€+2,430).

## 4 — Risk Register
Risk Register — Top 5 Delivery Risks (all rows have active mitigations — failure mode 2 fix)
# | Risk | L (1–5) | I (1–5) | Severity L×I | Expected cost (€) | Active mitigation
1 | Root-cause gate fails (< 40% allocation-driven): Phase 1–3 scope never triggers; €33K Phase 0 cost stranded | 3 | 5 | High | 9900 | Phase 0 is priced as a fixed-fee gate (€33K); if gate fails, engagement terminates — Meridian bears no Phase 1–3 cost. Commercial model (Hybrid) makes this explicit. Residual: EPAM absorbs mobilisation cost if gate fails after team is assembled.
2 | SAP ECC read-only credentials not provisioned by Day 5: Phase 1 start delayed, SA and DE1 burn rate with no productive output | 3 | 4 | High | 4500 | SAP access is a named client-side dependency in 02-solution.md with a right-to-pause clock in the contract. Delay triggers day-for-day timeline extension at no extra cost to Meridian; SA and DE1 are redeployed to available work during the wait. Buffer of 3 days priced in delivery impacts (Summary tab).
3 | POS data quality < 80% in both candidate countries: pilot restricted to one country, reducing statistical power of phantom-stock measurement | 3 | 3 | High | 2700 | Data quality gate is a named Phase 0 exit criterion. If both countries fail, EPAM restricts pilot to the higher-quality country at no scope-change cost. Root-cause diagnostic includes a 2-day POS completeness check before Phase 1 commit. Low additional cost — contained within contingency.
4 | Planner adoption < 30% at Phase 2 week 1 (after first OCM workshop): Phase 2 exit blocked, engagement extended | 3 | 4 | High | 3600 | EPAM Engagement Lead escalates to Meridian Programme Director within 24 hours of first-week accept-rate miss. Prosci sub-vendor runs remediation workshop within 5 business days (right-to-cure clause in sub-contractor MSA). Executive sponsor written mandate (client-side dependency A3) is precondition for Phase 2 start — if not in place, Phase 2 does not begin.
5 | Key person departure (ML Engineer or Data Engineer): named individual unavailable for ≥2 consecutive weeks mid-engagement | 2 | 4 | Medium | 1600 | EPAM names one pre-approved backup per key role in the proposal submission (named individual + CV + availability confirmation). Substitution requires Meridian approval within 3 business days; EPAM absorbs transition cost. Backup must have equivalent skill evidence to the primary named individual.
| TOTAL EXPECTED RISK COST |  |  |  | 22300 | Contingency set at 8% of delivery (8%) — 2× expected value coverage

## 5 — Assumption Register
Assumption Register — All bounded numerically or by named condition (failure mode 3 fix)
# | Assumption (bounded) | Consequence if false / contract treatment
A1 — SAP access by Day 5 | Meridian IT provisions SAP ECC read-only credentials to the EPAM dev environment within 5 business days of contract execution. Measurable: credentials confirmed by email receipt from Meridian IT lead. | If not received by Day 5: right-to-pause clock starts. Phase 1 start shifts day-for-day. No extra cost to Meridian; EPAM redeployment cost absorbed. If delay > 10 business days: either party may terminate Phase 1+ with 30-day written notice; only Phase 0 fixed fee is invoiced.
A2 — Root-cause gate ≥ 40% | Root-cause diagnostic confirms ≥ 40% of POS cancellations in the pilot country are attributable to allocation/visibility root cause (reason-code methodology agreed at Phase 0 kick-off; binding ruling within 2 business days if disputed). Measurable: percentage computed from agreed reason-code classification. | If gate fails (< 40%): engagement terminates at Phase 0. EPAM invoices fixed Phase 0 fee only (€33K). Full-rollout recommendation is not produced. Scope change to a different use case requires a new SOW.
A3 — Executive sponsor mandate before Phase 2 start | Meridian executive sponsor (named individual with authority to mandate planner participation) issues written mandate to ≥ 5 named planners in the pilot country before Phase 2 week 1. Measurable: signed memo or email from named sponsor received by EPAM PM before Phase 2 kick-off. | If written mandate not received: Phase 2 start is blocked. Each day of delay shifts timeline day-for-day at no extra cost. If mandate not received within 10 business days of Phase 1 close: EPAM escalates to Meridian CxO; unresolved after 5 more days is a programme-level stop.
A4 — Nearshore utilisation ≥ 75% from sprint 2 | EPAM nearshore engineers achieve ≥ 75% billable utilisation from sprint 2 (week 4 of engagement) onward. Measurable: weekly time-sheet extract reviewed at sprint close. If utilisation falls below 75% for 2 consecutive sprints, EPAM Delivery Director is notified. | If utilisation < 75% for 2 consecutive sprints: EPAM identifies root cause within 3 business days and presents a corrective action plan. If corrective action does not restore ≥ 75% within 1 sprint, EPAM replaces the under-utilised role at no extra cost to Meridian.
A5 — Prosci sub-vendor on-schedule delivery | Prosci sub-vendor delivers: (1) stakeholder mapping by end of Phase 0 week 2; (2) workshop 1 by Phase 2 week 1; (3) workshop 2 by Phase 2 week 3. Measurable: delivery date of each artefact against the named calendar date. | If any deliverable is > 3 business days late: EPAM Engagement Lead invokes right-to-cure clause in sub-contractor MSA; Prosci has 5 business days to deliver or provide a replacement resource. EPAM absorbs sub-contractor remediation cost within contingency. Meridian is not exposed to sub-vendor risk.

## 6 — Commercial Model
Commercial Model Decision — Hybrid recommended (failure mode 4 fix: T&M replaced)
Model | Risk fit | Cash-flow fit | Buyer fit (RFP §7)
Time & Materials (open-ended) | EPAM bears zero cost risk — all schedule and scope risk falls on Meridian. Root-cause gate creates unbounded exposure: Meridian pays whether or not the gate passes. | Meridian pays as-incurred; predictable for EPAM; unpredictable for buyer. | DISQUALIFYING — RFP §7 submission rules: 'open-ended T&M is a disqualifying condition.' Cannot be submitted.
Fixed Price (single lump sum) | EPAM bears all scope risk including root-cause gate variability and SAP integration unknowns. Both are high-uncertainty; pricing in a contingency to cover them inflates the fixed price above the €350K ceiling. | EPAM cash-flow risk: cost overruns eat margin and contingency simultaneously. Requires very high contingency to be viable — pushes total above cap. | RFP allows fixed-price but does not require it. Fixed price for a variable-scope engagement is a contract trap (see 02-review.md Critique 1).
Hybrid: Phase 0 fixed-fee + Phases 1–3 capped T&M ← RECOMMENDED | Phase 0 (€33K fixed): gate risk is Meridian's — if gate fails, they stop paying. Phases 1–3 (€307K capped T&M): EPAM carries cost risk within the cap; change-control triggers protect EPAM from scope creep. Each party carries the risk they can control. | Meridian knows maximum exposure (€340K all-in). Phase 0 is a low-risk first invoice before committing to full engagement. EPAM bills actuals up to cap. | COMPLIANT — RFP §7: 'fixed-price or capped T&M; no open-ended T&M overrun clauses.' Capped T&M with named change-control satisfies the constraint. Change-control triggers: root-cause gate scope change; POS data restriction to one country.
Recommendation
Recommend Hybrid: Phase 0 fixed-fee €33K (gated discovery) + Phases 1–3 capped T&M at €307K, total ceiling €340K. RATIONALE: the RFP explicitly prohibits open-ended T&M (disqualifying condition) and the root-cause gate creates a variable scope that makes a single fixed-price binding contract contractually dangerous (see 02-review.md, Critique 1 patch). Hybrid respects the RFP constraint ('capped T&M' is listed as permitted), aligns each party's risk with their control surface, and gives Meridian a known maximum exposure. The change-control mechanism (gate-failure scope change + POS data restriction to one country) is written into the contract as named triggers, not left as 'scope TBD at delivery'.