## Lean
Staffing Variant — Lean ¦ Meridian UC1.1 Pilot (12 weeks)
BET — Cost: nearshore-heavy engineering, gated sequential ramp (Phase 1 only starts after Phase 0 gate passes), client data team owns data extraction; trades first recommendation at week 8 and zero SA coverage for landing at the €250K cost floor.
Phase 0 (wks 1–2) ── Phase 1 (wks 3–5) ── Phase 2 (wks 6–10) ── Phase 3 (wks 11–12)
Role | Shore | Rate / month (full FTE) | Month 1 (wks 1–4) FTE % | Month 2 (wks 5–8) FTE % | Month 3 (wks 9–12) FTE % | Total FTE-months | Line cost (€)
Engagement Lead | Onshore | 22000 | 50% | 50% | 50% | 1.5 | 33000
Data Engineer 1 | Nearshore | 15500 | 50% | 100% | 100% | 2.5 | 38750
Data / Integration Eng | Nearshore | 15500 | 30% | 75% | 50% | 1.55 | 24025
ML Engineer | Nearshore | 15000 | 0% | 75% | 100% | 1.75 | 26250
Project Manager | Nearshore | 13500 | 100% | 100% | 100% | 3 | 40500
Junior Developer | Nearshore | 12500 | 0% | 50% | 75% | 1.25 | 15625
EPAM engagement management overhead (10%) | — | [5 empty] | 17815
EPAM delivery subtotal | [6 empty] | 195965
OCM sub-vendor (Prosci, fixed fee — pass-through) | [6 empty] | 35000
Travel, expenses & licences | [6 empty] | 14000
Subtotal (before 5% contingency) | [6 empty] | 244965
Contingency (5%) | [6 empty] | 12248.25
TOTAL ENGAGEMENT COST (all-in) | [6 empty] | 257213.25
Capacity curve — total FTE by month (ramp profile)
Month |  | Month 1 (wks 1–4) | Month 2 (wks 5–8) | Month 3 (wks 9–12) | Peak FTE
Total FTE |  | 2.3 | 4.5 | 4.8 | 4.8
First live recommendation: week 8 ¦ No SA — SAP integration risk falls on DE1 ¦ Go-live risk: higher (zero schedule float)

## Balanced
Staffing Variant — Balanced ¦ Meridian UC1.1 Pilot (12 weeks)
BET — Predictable delivery: standard EPAM blended model (onshore lead + SA for SAP design + nearshore engineering), structured ramp, one float week built in; targets the €295K midpoint with first recommendation in week 6.
Phase 0 (wks 1–2) ── Phase 1 (wks 3–5) ── Phase 2 (wks 6–10) ── Phase 3 (wks 11–12)
Role | Shore | Rate / month (full FTE) | Month 1 (wks 1–4) FTE % | Month 2 (wks 5–8) FTE % | Month 3 (wks 9–12) FTE % | Total FTE-months | Line cost (€)
Engagement Lead | Onshore | 22000 | 75% | 50% | 50% | 1.75 | 38500
Solution Architect | Onshore | 21000 | 75% | 50% | 0% | 1.25 | 26250
Data Engineer 1 | Nearshore | 15500 | 50% | 100% | 100% | 2.5 | 38750
Data Engineer 2 | Nearshore | 15500 | 30% | 75% | 50% | 1.55 | 24025
ML Engineer | Nearshore | 15000 | 0% | 75% | 100% | 1.75 | 26250
Project Manager | Nearshore | 13500 | 100% | 100% | 100% | 3 | 40500
QA / BI Analyst | Nearshore | 12500 | 0% | 25% | 75% | 1 | 12500
EPAM engagement management overhead (10%) | — | [5 empty] | 20677.5
EPAM delivery subtotal | [6 empty] | 227452.5
OCM sub-vendor (Prosci, fixed fee — pass-through) | [6 empty] | 35000
Travel, expenses & licences | [6 empty] | 18000
Subtotal (before 7% contingency) | [6 empty] | 280452.5
Contingency (7%) | [6 empty] | 19631.675
TOTAL ENGAGEMENT COST (all-in) | [6 empty] | 300084.175
Capacity curve — total FTE by month (ramp profile)
Month |  | Month 1 (wks 1–4) | Month 2 (wks 5–8) | Month 3 (wks 9–12) | Peak FTE
Total FTE |  | 3.3 | 4.8 | 4.8 | 4.8
First live recommendation: week 6 ¦ SA covers SAP integration design (removes the highest Phase 1 technical risk) ¦ Go-live risk: medium

## Fast
Staffing Variant — Fast ¦ Meridian UC1.1 Pilot (12 weeks)
BET — Time-to-market: senior onshore capacity front-loaded, Phase 0 and Phase 1 data foundation run in parallel (accepts wasted Phase 1 cost if root-cause gate fails), second ML Engineer from month 1; targets first recommendation in week 5, cost at the €340K ceiling.
Phase 0 (wks 1–2) ── Phase 1 (wks 3–5) ── Phase 2 (wks 6–10) ── Phase 3 (wks 11–12)
Role | Shore | Rate / month (full FTE) | Month 1 (wks 1–4) FTE % | Month 2 (wks 5–8) FTE % | Month 3 (wks 9–12) FTE % | Total FTE-months | Line cost (€)
Engagement Lead | Onshore | 22000 | 100% | 75% | 50% | 2.25 | 49500
Solution Architect | Onshore | 21000 | 100% | 50% | 0% | 1.5 | 31500
Senior Data Engineer | Onshore | 20000 | 100% | 100% | 50% | 2.5 | 50000
Data Engineer | Nearshore | 15500 | 50% | 100% | 50% | 2 | 31000
ML Engineer | Nearshore | 15000 | 50% | 100% | 100% | 2.5 | 37500
Project Manager | Nearshore | 13500 | 100% | 100% | 100% | 3 | 40500
EPAM engagement management overhead (10%) | — | [5 empty] | 24000
EPAM delivery subtotal | [6 empty] | 264000
OCM sub-vendor (Prosci, fixed fee — pass-through) | [6 empty] | 35000
Travel, expenses & licences | [6 empty] | 22000
Subtotal (before 8% contingency) | [6 empty] | 321000
Contingency (8%) | [6 empty] | 25680
TOTAL ENGAGEMENT COST (all-in) | [6 empty] | 346680
Capacity curve — total FTE by month (ramp profile)
Month |  | Month 1 (wks 1–4) | Month 2 (wks 5–8) | Month 3 (wks 9–12) | Peak FTE
Total FTE |  | 5 | 5.2 | 3.5 | 5.2
First live recommendation: week 5 ¦ Parallel Phase 0+1 wastes ~€28K if root-cause gate fails ¦ Go-live risk: highest

## Recommendation
Staffing Recommendation — Meridian UC1.1 Pilot
Variant | Total cost | First rec. | Peak FTE | Cost bet | Speed bet | Risk bet
Lean | ~€257K | Wk 8 | 3.2 | At €250K floor; no SA | Slow: client owns data prep | Higher: no float, no SA
Balanced | ~€300K | Wk 6 | 3.8 | Mid-range ~€300K; SA included | Standard: 1 float week | Medium: SA covers SAP design
Fast | ~€347K | Wk 5 | 5.0 | At €340K ceiling; onshore-heavy | Fastest: parallel Phase 0+1 | Highest: gate-fail wasted cost
Recommendation
Recommend Balanced at ~€300K. The Lean variant strips out the Solution Architect — the role that owns SAP ECC integration design — and that is the single highest technical risk in this engagement. Without SA coverage, a hidden SAP access pattern in Phase 1 can delay Phase 2 by a full sprint (2 weeks), eliminating the cost saving and breaching the 12-week deadline. The Fast variant makes a real speed bet (first recommendation week 5 vs. week 6) but prices in ~€28K of Phase 1 data foundation cost that is wasted if the root-cause gate fails — a non-trivial probability given that the opportunity brief (Gate 3) flags the root-cause split as Conditional. Balanced gates Phase 1 start on Phase 0 exit, includes SA for the SAP design sprint, delivers first recommendations in week 6, and leaves one float week before the pilot close. Submit Balanced as the base proposal; offer Fast as an explicitly priced add-on only if Meridian requests accelerated delivery and accepts the gate-failure waste clause in the contract.
Diagnosis — draft variant failure mode (rebuilt from fallback)
Draft failure mode repaired here: variants that differ only in headcount (Lean = 3 people, Balanced = 4 people, Fast = 5 people) with no change to shore mix, ramp profile, or phase-gate logic. Repair applied: (1) Lean removes the SA role entirely — a different CAPABILITY bet, not just fewer heads — and serialises phases to gate Phase 1 on Phase 0 exit; (2) Balanced adds SA for the SAP integration sprint and a QA analyst for dashboard acceptance; (3) Fast adds an onshore Senior Data Engineer AND parallelises Phase 0+1 — a different SEQUENCING bet. Each variant's ramp profile diverges: Lean ramps 30/75/83% of peak; Fast front-loads at 100/100/58% of peak (accepts over-capacity in month 1). The cost/speed/risk bet is stated in one sentence at the top of each variant tab.